## Sheet1
1 | Risk | Impact Description | Impact | Probability | Risk Score | Response | Mitigation Strategy | Contingency Plan | Responsible
1 | Functional Requirements missed during research & analysis phases. | Software Features missed from specification, impacting profitability and deadline of delivery of project. | 2 - Medium | 2 - Medium | 5 | Ensure extensive discovery phase of old system to identify requirements to set project scope. Schedule regular meetings with Product Owner to review scope of project and agree on change request timeline and budgets. | Conduct thorough reviews with Product Owner, establish clear scope, timelines and budget for changes. | Allocate reserve budget and time, prioritize essential features, plan for scope adjustments as needed. | Project Manager
2 | Incorrect Technology Product (Cloud, API Framework, UI Framework) chosen. | If a framework or cloud provider is chosen that is not fit for purpose, large sections of the project may have to be rebuilt. | 3 - High | 1 - Low | 3 | Research must be conducted after the requirements analysis phase to ensure the technical team's chosen technologies are suitable to meet the functional requirements of the project. | Perform technology compatibility checks post-requirements analysis to match project needs and functional criteria. | Prepare for alternative technology solutions, ensuring options align with project requirements. | Senior Developer
3 | Poor unit, end-to-end and integration tests. | If features & code is not thoroughly tested, bugs can be introduced that limit the usability of the product, leading to poor client satisfaction. | 3 - High | 2 - Medium | 6 | All business logic code needs to be unit tested. User stories must be end-to-end tested. External Services (Cloud, Database, API) must be integration tested. | Implement comprehensive testing strategy covering unit, end-to-end and integration tests for all components. | Prioritize critical tests, establish mock services for external dependencies, ensure rapid issue resolution. | Tester
4 | Reduced Operative productivity when migrating to new system. | As this system is directly tied to job performance & productivity in an existing high-throughput system, Operator need to be able to use the new system efficiently after launch. | 2 - Medium | 3 - High | 6 | Extensive user documentation must be written & training time must be allocated for each Operator, prior to a full-time release of the new system. | Develop user documentation and schedule training sessions well before system release. | Create quick reference guides and provide on-demand training support post-launch to address gaps. | Operations Director
5 | Cloud-Service deprecation. | While unlikely to happen during the project life-cycle, if the chosen Cloud Service Provider introduces breaking changes to their services, support will be required to ensure operability. | 4 - Critical | 2 - Medium | 8 | Long-term System support contracts should be drawn up and agreed upon to ensure system maintenance and support to accommodate breaking changes in services. | Negotiate long-term support contracts early, inluding maintenance and updates for service changes. | Establish a flexible support framework to adapt to unforeseen service disruptions or changes | Product Owner